## Sheet1
Backend Programming Estimate | [6 empty] | DIDL Product
| Hours | Cost/Hour | Total | Time | Person |  | Printed Book
|  |  |  | Estimate | Responsible |  | Reorganization
1. Printed Book Reorganization and Production | [6 empty] | Production
Design template for book |  |  |  |  | Dennis Chappell
Reorganize book | 481.5 |  |  |  | Nancy Hadley |  | Marketing
2. Marketing Materials Revision |  |  |  |  | Darby Hadley |  | Review Materials
3. Tutorial Automation |  |  |  | 3 months |  |  | Print Materials
XP | 546 | 15 | 8190 |  | Ryan Carraway
Vista/07 | 546 | 15 | 8190 |  | Darby Hadley |  | Tutorials
4. Multiple-Choice Test Engine | 70 | 65 | 4550 |  | George Draper | Functional | XP/Vista | Practice Tests - deliver all questions and answers in multiple formats
Exams - randomly select questions
5. Proficiency Task Delivery
Digitize task pages | 328.5 |  |  |  | Nancy Hadley |  | New (07)
Engine | 70 | 65 | 4550 |  | George Draper |  | under development |  | Web Page to deliver Tasks randomly
6. Database Development
Student Registration | 50 | 65 | 3250 |  | George Draper |  | Student registration system
7. Reporting
Student | 50 | 65 | 3250 |  | George Draper | Partially functional
Administrative | 60 | 65 | 3900 |  | George Draper |  | Web Page interface
8. Payment Collection | 5 | 65 | 325 |  | George Draper |  | Manually collected by Nancy
9. Security | 10 | 65 | 650 |  | George Draper | Functional
10. Other Web Pages | 20 | 65 | 1300 |  | George Draper
11. Project Coordination |  |  |  |  | Nancy Hadley
Database to house results
Total |  |  | 38155 |  |  |  | Email system for grading tasks
Grading task support system
Database Development
Student Registration
Administrative
Web Site Security
[6 empty] | Functional | Public Web Pages
Reporting
Student tracking
Administrative tracking
Web Site Payment
Pay-pal type services
System to determine and track billing
Billing System
Large client billing